## Sheet1
Work Plan for the Development of the Online Tool for Visualisation of the MLSS Data
|  | November |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March
|  | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3
Phase | Activity
Inception | Inception report | bar: November W3 to December W1
Agree on concept | bar: December W1
Set up | Prioritization of indicators | bar: January W2
Agree on naming protocols of variables | bar: January W2
Definition of secondary sources | bar: January W3
Inspection and tests to the data | bar: January W3
Transformation of the data to relational | bar: January W3 to January W4
Program of User Interface | bar: January W4 to February W1
Program reactivity of elements | bar: February W1 to February W3
Style User Interface | bar: February W2
Set up server and domain | bar: February W4
Test addition of new rounds of data | bar: February W4
Test of User Experience | bar: February W4 to March W1
Pilot app with internal users | bar: February W4 to March W1
Documentation | Documentation for users to navigate | bar: March W2 to March W3
Documentation for administrators | bar: March W2 to March W3
Sensitization | Workshops for administrators and users | bar: March W3
Brief report | bar: March W3